## 2022 Review
5/1/2023, Version 3.0 - Review 2022 by the SIREUS team
Who is responsible for the activity?
P = Project Group with SACC-USA in House of Sweden
(P coordinates other units within SACC-USA, SACC Regional Chambers, The Embassy, SI and other Team Sweden efforts) | [8 empty] | = Map, inventory,… |  |  |  | = Not done yet
S = Resource in Sweden for contacts with business and relevant organisations.
U = Resources at Swedish Universities to be involved in the project | [8 empty] | = Identify, analyse |  |  |  | = Started, partially
Is the activity mutual or individual?
M = Mutual, activity carried out for the universities as a group | [8 empty] | = Visit, organize, … |  |  |  | = Done
I = Individually, activity performed for individual universities
= Postponed
[11 empty] | Abcdef |  | = New activity
Goals and activities for SIREUS - "Platform for increased talent mobility and knowledge exchange between Sweden and the U.S.
Goal | Sub-goal number | Sub-goal | Activity number | Activity | Who? | M | I | Q2 2022 | Q3 2022 | Q4 2022 | Q1 2023 | Q2 2023 | Q3 2023 | Q4 2023 | H1 2024 | H2 2024
1. Strengthen the collaboration between Swedish universities and the Swedish-American business community
| 1.1 | Find synergies between Swedish universities and SACC Regional Chambers (Applicable for all GOALS)
|  |  | 1.1.0 | Before mapping of business contacts. It needed to be agreed on thematic areas that SIREUS will focus on. | P | X
|  |  | 1.1.1 | Map the existing collaborations between Regional Chambers and universities concerning exchange studies, business contacts and research collaboration | P | X
|  |  | 1.1.2 | Each university appoints a contact person and sets aside time to identify its existing exchange programs, business contacts and research collaborations | U |  | X
|  |  | 1.1.3 | Identify synergies that can be used and developed between Regional Chambers and the universities. | P | X | X
| 1.2 | Identify and develop Swe-Am exchange programs, business contacts and research collaborations
|  |  | 1.2.1 | Map existing contacts between participating universities and companies in Sweden and the U.S. | P | X | X
|  |  | 1.2.2 | Map any existing research collaborations (involving companies in Sweden and the U.S.) | P | X
|  |  | 1.2.3 | Identify connections that can be used | P | X
|  |  | 1.2.4 | Map business contacts that the SACC Network can provide | P |  | X
|  |  | 1.2.5 | What does each university prioritize to develop with regards to their U.S. strategy? | P, U |  | X
|  |  | 1.2.6 | Identify companies outside of the SACC network based on specific skill/industry, (e.g. marine research) | P | X | X
|  |  | 1.2.7 | Personally visit the participating universities to present, inform and answer questions within the project | S |  | X
|  |  | 1.2.8 | Introduction and maintenance of the contacts between Swedish universities and American companies | P, S, U |  | X
| 1.3 | Increase the attractiveness of the echange programs by offering internships in connection with the studies, in both directions
|  |  | 1.3.1 | From previous mapping of the universities' business contacts, (1.2.1), identify companies interested in offering internships | P, U |  | X
|  |  | 1.3.2 | From previous mapping of business contacts via the SACC network (1.2.4), identify companies interested in offering internships | P, U |  | X
|  |  | 1.3.3 | What individual requests/strategies do the universities prioritize, and what efforts should the project be concentrated on? | P, U |  | X
|  |  | 1.3.4 | Identify the unique strength/strenghts of the universities (smart cities, marine science, arctic research, gaming, etc) | U |  | X
|  |  | 1.3.5 | Identify new companies external to SACC based on specific skills/industry, (e.g. marine research) | P | X | X
|  |  | 1.3.6 | Introduce contacts to initiate new collaborations for internships in connection with the studies, in both directions. | P | X | X
| 1.4 | Make it possible for Swedish students to do their thesis with American companies
|  |  | 1.4.1 | From previous mapping of business contacts (1.2.1), identify companies intrested in offering Capstone jobs | P |  | X
|  |  | 1.4.2 | Identify the specific skills of the students to match them with the right company | U |  | X
|  |  | 1.4.3 | Contact companies in the U.S. for internships and thesis jobs. Outreach activities. | P |  | X
2. Strengthen the collaboration and mobility between Swedish and American universities
| 2.1 | Identify and develop Swedish-American exchange programs, business contacts and research collaborations (ref Goal 1.2)
|  |  | 2.1.1 | Map the existing exchange programs (different categories) | P |  | X
|  |  | 2.1.2 | What does each university prioritize to develop with regards to their U.S. strategy? | U |  | X
| 2.2 | Create and strengthen existing collaborations between Swedish and American universities
|  |  | 2.2.1 | What are the existing contacts between Swedish and American universities? | U |  | X
|  |  | 2.2.2 | What univeristy contacts can the SACC network and the Embassy provide? | P |  | X
|  |  | 2.2.3 | What individual objectives/strategies/areas should the project concentrate on? | P, U |  | X
|  |  | 2.2.4 | Map American career fairs that can be relevant for swedish universities according to the respective university's U.S. strategy and interest sphere | P | X | X
|  |  | 2.2.5 | Inform about bilateral programs, courses and internships during meetings and fairs | P | X
|  |  | 2.2.6 | Organize and host delegation travels to American universities to examine possibilities of collaboration | P | X | X
|  |  | 2.2.7 | Organize SIREUS forums to establish and maintain contacts between Swedish and American universities
| 2.3 | Identify, educate and coordinate ambassadors for talent mobility (Clarify the role of ambassadors)
|  |  | 2.3.1 | Identify Swedish researchers and professors with the respective participating universities that are active in, or interested in, the U.S. | P, U |  | X
|  |  | 2.3.2 | Together with IFHU, STARS and STINT identify Swedish researchers and professors active in the U.S. | P, U | X
|  |  | 2.3.3 | Together with IFHU, STARS and STINT identify American researchers and teachers that are active in Sweden | P, U | X
|  |  | 2.3.4 | Together with IFHU, STARS and STINT identify Swedish researchers and teachers that are interested in the U.S. | P, U | X
|  |  | 2.3.5 | Together with IFHU, STARS and STINT identify American researchers and professors interested in Sweden | P | X
|  |  | 2.3.6 | Educate, coordinate and create meeting places for ambassadors for talent mobility | P | X
|  |  | 2.3.7 | Use House of Sweden as a meeting place for ambassadors for talent mobility | P | X
3. Strengthen the bilateral collaboration concerning research, innovation and entepreneurship
| 3.1 | Identify and develop Swe-Am exchange programs, business contacts and research collaborations (ref Goal 1.2)
|  |  | 3.1.1 | Map and communicate the existing research collaborations at the universities | P | X
|  |  | 3.1.2 | Which areas are prioritized for developement for each university according to their U.S. strategy? | P |  | X
|  |  | 3.1.3 | How can the SACC network and other Team Sweden stakeholders assist with contacts with researchers with regional American universities? | P |  | X
|  |  | 3.1.4 | Introduce and connect SACC members intrested in innovation and entrepreneurship | P |  | X
|  |  | 3.1.5 | As a Team Sweden stakeholder, actively communicate Sweden as an innovation country | P | X
|  |  | 3.1.6 | Develop and initiate research collaborations between companies and universities. | P | X | X
| 3.2 | Build an information portal for the platform
|  |  | 3.2.1 | Create an information portal concerning bilateral programs, courses and internships | P | X
|  |  | 3.2.2 | Include information about research, innovation and entrepreneurship in the information portal | P | X
|  |  | 3.2.3 | Describe collaborations and success stories in the project | P | X
|  |  | 3.2.4 | Include FAQ, Community Chat and other relevant information and function in the information portal | P | X
| 3.3 | Create meeting places for researchers, businesses, students and investors
|  |  | 3.3.1 | Engage with STINT | P | X
|  |  | 3.3.2 | Connect the program with STARS | P | X
|  |  | 3.3.3 | Together with the Embassy/IFHU, profile House of Sweden as an innovation center | P | X
|  |  | 3.3.4 | Establish and schedule suggestions for relevant seminars, workshops and webinars in House of Sweden | P | X
|  |  | 3.3.5 | Organize "SIREUS RESEARCH forums" to establish and maintain research collaborations between the Swedish and Amrican universites
4. Strengthen Sweden's attractiveness as a destination for American students and researchers
| 4.1 | Recruit more students to Sweden by marketing Sweden as a destination for studies
|  |  | 4.1.0 | Define career fair vs. student fairs and map existing market possibilities | P | X
|  |  | 4.1.1 | Attend regional career fairs/ student fairs in the U.S. | P | X
|  |  | 4.1.2 | Implement, communicate and strengthen marketing material from the Swedish Institute (Team Sweden activity) to American universities and students. | P | X
|  |  | 4.1.3 | Organize Study in Sweden student fairs together with the Swedish Institute, regional chambers and affiliated universities
| 4.2 | Make an inventory and communicate private and public scholarships for studies/research, in both countries
|  |  | 4.2.1 | Make an inventory and compile information about relevant private and public scholarships for studies/research | P, S | X
|  |  | 4.2.2 | Include information about scholarships in the information portal | P | X
|  |  | 4.2.3 | Add scholarships for internships (not just studies/research), specifically for internships with SACC Chambers | P | X
|  |  | 4.2.4 | Contact scholarship foundations concerning new collaborations. | S, U |  | X
| 4.3 | Increase the attractiveness of the study destination by offering internships in connection with the studies
|  |  | 4.3.1 | Which business contacts to the universities already have locally | S, U | X
|  |  | 4.3.2 | Which business contacts can the SACC network assist with? | S |  | X
|  |  | 4.3.3 | Which areas of study do the universities want to prioritize? | S, U |  | X
|  |  | 4.3.4 | Visit local companies and market the concept of American students as interns | S | X
| 4.4 | Facilitate for Swedish universities to become certified to process Am student loans, FAFSA, and other certification
|  |  | 4.4.1 | Certified Swe universities share experiences with other participating universities | P | X
|  |  | 4.4.2 | Work to increase the interest of other Swedish universities to become certified for handling FAFSA | P | X
| 4.5 | Create an active and relevant social media presence aimed at American students
|  |  | 4.5.1 | Establish a social media presence for the University Platform | P | X
|  |  | 4.5.2 | Create campaigns that target American students | P | X
|  |  | 4.5.3 | Become active at American student portals. | P | X
|  |  | 4.5.4 | Create an easy way (e.g. FAQ) to answer questions about Sweden as a destination for studies | P | X
|  |  | 4.5.5 | Establish SIREUS forum as a marketing label on social media channels

## Version 3.0 (081922)
8/19/2022, Version 3.0 - compiled by Christer Bergman
Who is responsible for the activity?
P = Project Group with SACC-USA in House of Sweden
(P coordinates other units within SACC-USA, SACC Regional Chambers, The Embassy, SI and other Team Sweden efforts) | [8 empty] | = Map, inventory,…
S = Resource in Sweden for contacts with business and relevant organisations.
U = Resources at Swedish Universities to be involved in the project | [8 empty] | = Identify, analyse
Is the activity mutual or individual?
M = Mutual, activity carried out for the universities as a group | [8 empty] | = Visit, organize, …
I = Individually, activity performed for individual universities
Goals and activities for SIREUS - "Platform for increased talent mobility and knowledge exchange between Sweden and the U.S.
Goal | Sub-goal number | Sub-goal | Activity number | Activity | Who? | M | I | Q2 2022 | Q3 2022 | Q4 2022 | H1 2023 | H2 2023 | 2024
1. Strengthen the collaboration between Swedish universities and the Swedish-American business community
| 1.1 | Find synergies between Swedish universities and SACC Regional Chambers (Applicable for all GOALS)
|  |  | 1.1.1 | Map the existing collaborations between Regional Chambers and universities concerning exchange studies, business contacts and research collaboration | P | X
|  |  | 1.1.2 | Each university appoints a contact person and sets aside time to identify its existing exchange programs, business contacts and research collaborations | U |  | X
|  |  | 1.1.3 | Identify synergies that can be used and developed between Regional Chambers and the universities. | P | X | X
| 1.2 | Identify and develop Swe-Am exchange programs, business contacts and research collaborations
|  |  | 1.2.1 | Map existing contacts between participating universities and companies in Sweden and the U.S. | P | X | X
|  |  | 1.2.2 | Map any existing research collaborations (involving companies in Sweden and the U.S.) | P | X
|  |  | 1.2.3 | Identify connections that can be used | P | X
|  |  | 1.2.4 | Map business contacts that the SACC Network can provide | P |  | X
|  |  | 1.2.5 | What does each university prioritize to develop with regards to their U.S. strategy? | P, U |  | X
|  |  | 1.2.6 | Identify companies outside of the SACC network based on specific skill/industry, (e.g. marine research) | P | X | X
|  |  | 1.2.7 | Personally visit the participating universities to present, inform and answer questions within the project | S |  | X
|  |  | 1.2.8 | Introduction and maintenance of the contacts between Swedish universities and American companies | P, S, U |  | X
| 1.3 | Increase the attractiveness of the echange programs by offering internships in connection with the studies, in both directions
|  |  | 1.3.1 | From previous mapping of the universities' business contacts, (1.2.1), identify companies interested in offering internships | P, U |  | X
|  |  | 1.3.2 | From previous mapping of business contacts via the SACC network (1.2.4), identify companies interested in offering internships | P, U |  | X
|  |  | 1.3.3 | What individual requests/strategies do the universities prioritize, and what efforts should the project be concentrated on? | P, U |  | X
|  |  | 1.3.4 | Identify the unique strength/strenghts of the universities (smart cities, marine science, arctic research, gaming, etc) | U |  | X
|  |  | 1.3.5 | Identify new companies external to SACC based on specific skills/industry, (e.g. marine research) | P | X | X
|  |  | 1.3.6 | Introduce contacts to initiate new collaborationsfor internships in connection with the studies, in both directions. | P | X | X
| 1.4 | Make it possible for Swedish students to do their thesis with American companies
|  |  | 1.4.1 | From previous mapping of business contacts (1.2.1), identify companies intrested in offering Capstone jobs | P |  | X
|  |  | 1.4.2 | Identify the specific skills of the students to match them with the right company | U |  | X
|  |  | 1.4.3 | Contact companies in the U.S. for internships and thesis jobs. Outreach activities. | P |  | X
2. Strengthen the collaboration and mobility between Swedish and American universities
| 2.1 | Identify and develop Swedish-American exchange programs, business contacts and research collaborations (ref Goal 1.2)
|  |  | 2.1.1 | Map the existing exchange programs (different categories) | P |  | X
|  |  | 2.1.2 | What does each university prioritize to develop with regards to their U.S. strategy? | U |  | X
| 2.2 | Create and strengthen existing collaborations between Swedish and American universities
|  |  | 2.2.1 | What are the existing contacts between Swedish and American universities? | U |  | X
|  |  | 2.2.2 | What univeristy contacts can the SACC network and the Embassy provide? | P |  | X
|  |  | 2.2.3 | What individual objectives/strategies/areas should the project concentrate on? | P, U |  | X
|  |  | 2.2.4 | Map American career fairs that can be relevant for swedish universities according to the respective university's U.S. strategy and interest sphere | P | X | X
|  |  | 2.2.5 | Inform about bilateral programs, courses and internships during meetings and fairs | P | X
|  |  | 2.2.6 | Organize and host delegation travels to American universities to examine possibilities of collaboration | P | X | X
| 2.3 | Identify, educate and coordinate ambassadors for talent mobility (Clarify the role of ambassadors)
|  |  | 2.3.1 | Identify Swedish researchers and professors with the respective participating universities that are active in, or interested in, the U.S. | P, U |  | X
|  |  | 2.3.2 | Together with IFHU, STARS and STINT identify Swedish researchers and professors active in the U.S. | P, U | X
|  |  | 2.3.3 | Together with IFHU, STARS and STINT identify American researchers and teachers that are active in Sweden | P, U | X
|  |  | 2.3.4 | Together with IFHU, STARS and STINT identify Swedish researchers and teachers that are interested in the U.S. | P, U | X
|  |  | 2.3.5 | Together with IFHU, STARS and STINT identify American researchers and professors interested in Sweden | P | X
|  |  | 2.3.6 | Educate, coordinate and create meeting places for ambassadors for talent mobility | P | X
|  |  | 2.3.7 | Use House of Sweden as a meeting place for ambassadors for talent mobility | P | X
3. Strengthen the bilateral collaboration concerning research, innovation and entepreneurship
| 3.1 | Identify and develop Swe-Am exchange programs, business contacts and research collaborations (ref Goal 1.2)
|  |  | 3.1.1 | Map and communicate the existing research collaborations at the universities | P | X
|  |  | 3.1.2 | Which areas are prioritized for developement for each university according to their U.S. strategy? | P |  | X
|  |  | 3.1.3 | How can the SACC network and other Team Sweden stakeholders assist with contacts with researchers with regional American universities? | P |  | X
|  |  | 3.1.4 | Introduce and connect SACC members intrested in innovation and entrepreneurship | P |  | X
|  |  | 3.1.5 | As a Team Sweden stakeholder, actively communicate Sweden as an innovation country | P | X
|  |  | 3.1.6 | Develop and initiate research collaborations between companies and universities. | P | X | X
| 3.2 | Build an information portal for the platform
|  |  | 3.2.1 | Create an information portal concerning bilateral programs, courses and internships | P | X
|  |  | 3.2.2 | Include information about research, innovation and entrepreneurship in the information portal | P | X
|  |  | 3.2.3 | Describe collaborations and success stories in the project | P | X
|  |  | 3.2.4 | Include FAQ, Community Chat and other relevant information and function in the information portal | P | X
| 3.3 | Create meeting places for researchers, businesses, students and investors
|  |  | 3.3.1 | Engage with STINT | P | X
|  |  | 3.3.2 | Connect the program with STARS | P | X
|  |  | 3.3.3 | Together with the Embassy/IFHU, profile House of Sweden as an innovation center | P | X
|  |  | 3.3.4 | Establish and schedule suggestions for relevant seminars, workshops and webinars in House of Sweden | P | X
4. Strengthen Sweden's attractiveness as a destination for American students and researchers
| 4.1 | Recruit more students to Sweden by marketing Sweden as a destination for studies
|  |  | 4.1.1 | Attend regional career fairs in the U.S. | P | X
|  |  | 4.1.2 | Implement, communicate and strengthen marketing material from the Swedish Institute (Team Sweden activity) to American universities and students. | P | X
| 4.2 | Make an inventory and communicate private and public scholarships for studies/research, in both countries
|  |  | 4.2.1 | Make an inventory and compile information about relevant private and public scholarships for studies/research | P, S | X
|  |  | 4.2.2 | Include information about scholarships in the information portal | P | X
|  |  | 4.2.3 | Add scholarships for internships (not just studies/research), specifically for internships with SACC Chambers | P | X
|  |  | 4.2.4 | Contact scholarship foundations concerning new collaborations. | S, U |  | X
| 4.3 | Increase the attractiveness of the study destination by offering internships in connection with the studies
|  |  | 4.3.1 | Which business contacts to the universities already have locally | S, U | X
|  |  | 4.3.2 | Which business contacts can the SACC network assist with? | S |  | X
|  |  | 4.3.3 | Which areas of study do the universities want to prioritize? | S, U |  | X
|  |  | 4.3.4 | Visit local companies and market the concept of American students as interns | S | X
| 4.4 | Facilitate for Swedish universities to become certified to process Am student loans, FAFSA, and other certification
|  |  | 4.4.1 | Certified Swe universities share experiences with other participating universities | P | X
|  |  | 4.4.2 | Work to increase the interest of other Swedish universities to become certified for handling FAFSA | P | X
| 4.5 | Create an active and relevant social media presence aimed at American students
|  |  | 4.5.1 | Establish a social media presence for the University Platform | P | X
|  |  | 4.5.2 | Create campaigns that target American students | P | X
|  |  | 4.5.3 | Become active at American student portals. | P | X
|  |  | 4.5.4 | Create an easy way (e.g. FAQ) to answer questions about Sweden as a destination for studies | P | X

## Version 2.0 (041822) w changes
8/19/2022, Version 3.0 - compiled by Christer Bergman
Who is responsible for the activity?
P = Project Group with SACC-USA in House of Sweden
(P coordinates other units within SACC-USA, SACC Regional Chambers, The Embassy, SI and other Team Sweden efforts) | [8 empty] | = Map, inventory,…
S = Resource in Sweden for contacts with business and relevant organisations.
U = Resources at Swedish Universities to be involved in the project | [8 empty] | = Identify, analyse
Is the activity mutual or individual?
M = Mutual, activity carried out for the universities as a group | [8 empty] | = Visit, organize, …
I = Individually, activity performed for individual universities
Goals and activities for SIREUS - "Platform for increased talent mobility and knowledge exchange between Sweden and the U.S.
Goal | Sub-goal number | Sub-goal | Activity number | Activity | Who? | M | I | Q2 2022 | Q3 2022 | Q4 2022 | H1 2023 | H2 2023 | 2024
1. Strengthen the collaboration between Swedish universities and the Swedish-American business community
| 1.1 | Find synergies between Swedish universities and SACC Regional Chambers (Applicable for all GOALS)
|  |  | 1.1.1 | Map the existing collaborations between Regional Chambers and universities concerning exchange studies, business contacts and research collaboration | P | X
|  |  | 1.1.2 | Each university appoints a contact person and sets aside time to identify its existing exchange programs, business contacts and research collaborations | U |  | X
|  |  | 1.1.3 | Identify synergies that can be used and developed between Regional Chambers and the universities. | P | X | X
| 1.2 | Identify and develop Swe-Am exchange programs, business contacts and research collaborations
|  |  | 1.2.1 | Map existing contacts between participating universities and companies in Sweden and the U.S. | P | X | X
|  |  | 1.2.2 | Map any existing research collaborations (involving companies in Sweden and the U.S.) | P | X
|  |  | 1.2.3 | Identify connections that can be used | P | X
|  |  | 1.2.4 | Map business contacts that the SACC Network can provide | P, U |  | X
|  |  | 1.2.5 | What does each university prioritize to develop with regards to their U.S. strategy? | P, U |  | X
|  |  | 1.2.6 | Identify companies outside of the SACC network based on specific skill/industry, (e.g. marine research) | P | X | X
|  |  | 1.2.7 | Personally visit the participating universities to present, inform and answer questions within the project | S |  | X
|  |  | 1.2.8 | Introduction and maintenance of the contacts between Swedish universities and American companies | P, S, U |  | X
| 1.3 | Increase the attractiveness of the echange programs by offering internships in connection with the studies, in both directions
|  |  | 1.3.1 | From previous mapping of the universities' business contacts, (1.2.1), identify companies interested in offering internships | P, U |  | X
|  |  | 1.3.2 | From previous mapping of business contacts via the SACC network (1.2.4), identify companies interested in offering internships | P, U |  | X
|  |  | 1.3.3 | What individual requests/strategies do the universities prioritize, and what efforts should the project be concentrated on? | P, U |  | X
|  |  | 1.3.4 | Identify the unique strength/strenghts of the universities (smart cities, marine science, arctic research, gaming, etc) | U |  | X
|  |  | 1.3.5 | Identify new companies external to SACC based on specific skills/industry, (e.g. marine research) | P | X | X
|  |  | 1.3.6 | Introduce contacts to initiate new collaborationsfor internships in connection with the studies, in both directions. | P | X | X
| 1.4 | Make it possible for Swedish students to do their thesis with American companies
|  |  | 1.4.1 | From previous mapping of business contacts (1.2.1), identify companies intrested in offering Capstone jobs | P |  | X
|  |  | 1.4.2 | Identify the specific skills of the students to match them with the right company | U |  | X
|  |  | 1.4.3 | Contact companies in the U.S. for internships and thesis jobs. Outreach activities. | P |  | X
2. Strengthen the collaboration and mobility between Swedish and American universities
| 2.1 | Identify and develop Swedish-American exchange programs, business contacts and research collaborations (ref Goal 1.2)
|  |  | 2.1.1 | Map the existing exchange programs (different categories) | P |  | X
|  |  | 2.1.2 | What does each university prioritize to develop with regards to their U.S. strategy? | U |  | X
| 2.2 | Create and strengthen existing collaborations between Swedish and American universities
|  |  | 2.2.1 | What are the existing contacts between Swedish and American universities? | U |  | X
|  |  | 2.2.2 | What univeristy contacts can the SACC network and the Embassy provide? | P |  | X
|  |  | 2.2.3 | What individual objectives/strategies/areas should the project concentrate on? | P, U |  | X
|  |  | 2.2.4 | Map American career fairs that can be relevant for swedish universities according to the respective university's U.S. strategy and interest sphere | P | X | X
|  |  | 2.2.5 | Inform about bilateral programs, courses and internships during meetings and fairs | P | X
|  |  | 2.2.6 | Organize and host delegation travels to American universities to examine possibilities of collaboration | P | X | X
| 2.3 | Identify, educate and coordinate ambassadors for talent mobility (Clarify the role of ambassadors)
|  |  | 2.3.1 | Identify Swedish researchers and professors with the respective participating universities that are active in, or interested in, the U.S. | P, U |  | X
|  |  | 2.3.2 | Together with IFHU, STARS and STINT identify Swedish researchers and professors active in the U.S. | P, U | X
|  |  | 2.3.3 | Together with IFHU, STARS and STINT identify American researchers and teachers that are active in Sweden | P, U | X
|  |  | 2.3.4 | Together with IFHU, STARS and STINT identify Swedish researchers and teachers that are interested in the U.S. | P, U | X
|  |  | 2.3.5 | Together with IFHU, STARS and STINT identify American researchers and professors interested in Sweden | P | X
|  |  | 2.3.6 | Educate, coordinate and create meeting places for ambassadors for talent mobility | P | X
|  |  | 2.3.7 | Use House of Sweden as a meeting place for ambassadors for talent mobility | P | X
3. Strengthen the bilateral collaboration concerning research, innovation and entepreneurship
| 3.1 | Identify and develop Swe-Am exchange programs, business contacts and research collaborations (ref Goal 1.2)
|  |  | 3.1.1 | Map and communicate the existing research collaborations at the universities | P | X
|  |  | 3.1.2 | Which areas are prioritized for developement for each university according to their U.S. strategy? | P |  | X
|  |  | 3.1.3 | How can the SACC network and other Team Sweden stakeholders assist with contacts with researchers with regional American universities? | P |  | X
|  |  | 3.1.4 | Introduce and connect SACC members intrested in innovation and entrepreneurship | P |  | X
|  |  | 3.1.5 | As a Team Sweden stakeholder, actively communicate Sweden as an innovation country | P | X
|  |  | 3.1.6 | Develop and initiate research collaborations between companies and universities. | P | X | X
| 3.2 | Build an information portal for the platform
|  |  | 3.2.1 | Create an information portal concerning bilateral programs, courses and internships | P | X
|  |  | 3.2.2 | Include information about research, innovation and entrepreneurship in the information portal | P | X
|  |  | 3.2.3 | Describe collaborations and success stories in the project | P | X
|  |  | 3.2.4 | Include FAQ, Community Chat and other relevant information and function in the information portal | P | X
| 3.3 | Create meeting places for researchers, businesses, students and investors
|  |  | 3.3.1 | Engage with STINT | P | X
|  |  | 3.3.2 | Connect the program with STARS | P | X
|  |  | 3.3.3 | Together with the Embassy/IFHU, profile House of Sweden as an innovation center | P | X
|  |  | 3.3.4 | Establish and schedule suggestions for relevant seminars, workshops and webinars in House of Sweden | P | X
4. Strengthen Sweden's attractiveness as a destination for American students and researchers
| 4.1 | Recruit more students to Sweden by marketing Sweden as a destination for studies
|  |  | 4.1.1 | Attend regional career fairs in the U.S. | P | X
|  |  | 4.1.2 | Implement, communicate and strengthen marketing material from the Swedish Institute (Team Sweden activity) to American universities and students. | P | X
| 4.2 | Make an inventory and communicate private and public scholarships for studies/research, in both countries
|  |  | 4.2.1 | Make an inventory and compile information about relevant private and public scholarships for studies/research | P, S | X
|  |  | 4.2.2 | Include information about scholarships in the information portal | P | X
|  |  | 4.2.3 | Add scholarships for internships (not just studies/research), specifically for internships with SACC Chambers | P | X
|  |  | 4.2.4 | Contact scholarship foundations concerning new collaborations. | S, U |  | X
| 4.3 | Increase the attractiveness of the study destination by offering internships in connection with the studies
|  |  | 4.3.1 | Which business contacts to the universities already have locally | S, U | X
|  |  | 4.3.2 | Which business contacts can the SACC network assist with? | S |  | X
|  |  | 4.3.3 | Which areas of study do the universities want to prioritize? | S, U |  | X
|  |  | 4.3.4 | Visit local companies and market the concept of American students as interns | S | X
| 4.4 | Facilitate for Swedish universities to become certified to process Am student loans, FAFSA, and other certification
|  |  | 4.4.1 | Certified Swe universities share experiences with other participating universities | P | X
|  |  | 4.4.2 | Work to increase the interest of other Swedish universities to become certified for handling FAFSA | P | X
| 4.5 | Create an active and relevant social media presence aimed at American students
|  |  | 4.5.1 | Establish a social media presence for the University Platform | P | X
|  |  | 4.5.2 | Create campaigns that target American students | P | X
|  |  | 4.5.3 | Become active at American student portals. | P | X
|  |  | 4.5.4 | Create an easy way (e.g. FAQ) to answer questions about Sweden as a destination for studies | P | X